## Agile Project Plan
AGILE PROJECT PLAN TEMPLATE
| PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE
| File Utility | Chockkalingam | 2020-09-20 | 2020-10-03 |  | 20% |  | SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
| Sprint 1 |  | Chockkalingam |  | 2020-09-21 | 2020-09-25 | 4 | Complete
| Project and Environment Setup |  | Chockkalingam |  | 2020-09-21 | 2020-09-22 | 1 | Complete
| Menu & Sub Menu Options creation and testing |  | Chockkalingam |  | 2020-09-22 | 2020-09-23 | 1 | Complete
| Coding and Testing for Listing of file names |  | Chockkalingam |  | 2020-09-23 | 2020-09-25 | 2 | Complete
| Sprint 2 |  | Chockkalingam |  | 2020-09-28 | 2020-10-02 | 4 | Complete
| Coding and Testing for adding and deleting of file names |  | Chockkalingam |  | 2020-09-28 | 2020-09-29 | 1 | Complete
| Coding and Testing for searching of file names |  | Chockkalingam |  | 2020-09-29 | 2020-09-30 | 1 | Complete
| Documentation for installation and execution |  | Chockkalingam |  | 2020-09-30 | 2020-10-02 | 2 | Complete
CLICK HERE TO CREATE IN SMARTSHEET

## Agile Project Plan - BLANK
AGILE PROJECT PLAN TEMPLATE
| PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE
SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
Sprint 1
Feature 1
Feature 2
Feature 3
Sprint 2
Feature 4
Feature 5
Feature 6
Sprint 3
Feature 7
Feature 8
Feature 9

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.